## Slide 1: Campus Executives February 6, 2013

## Slide 2: Agenda
Welcome – Brian Cohen and Ron Spalter
Project Update – Suman Taneja
March Releases
July Release
Senior College Procurement – Satish Mishra
December Releases
Campus Solutions – Jim Anastasio
W3 Academic – W2 FA/WS – Graduate Admissions
Asset Management and Payroll – Satish Mishra
Best Practices & Lessons to share from the Colleges

## Slide 3: What’s Complete/What’s Ahead
* = Design Activities to begin in June 2013

## Slide 4: What’s Complete/What’s Ahead
* = Design Activities to begin in June 2013

## Slide 5: Potential and Realized Benefits
Benefit | Comments /“What the Users are saying”
Working towards retiring aging, unsupportable, difficult to modify systems | CUPS personnel system was retired in 2009 TIF and SIMS targeted to retire in the next 18 months A common Procurement system – opportunity to retire disparate shadow systems in the next 12 months Insight asset management system targeted to retire in 12 months
Foundation for data driven decision making | “single point of access…that provides services and relevant information between all institutions” “Students have more access and control of their information” “one of the most important benefits of CUNYfirst is that all data is in real-time….”
Opportunity to assess and re-engineer business process | “…it requires us to look at internal controls and ensure they are adequate and efficient…” “…allows us to look at the business process to see if we are able to do it better”
Improved security of data compliant with FERPA and reducing risk of identity theft | “The EMPLID replaces Social Security Number – therefore protecting student sensitive information”

## Slide 6: CUNYfirst Community Survey
2012 Key Findings
Responses – 3,189
70% stated their Senior Leadership is committed to the Project
Communication is improving for the Project overall and at the College level
Greater likeability of system among frequent users (60% weekly vs. 49% quarterly)
60% stated using CUNYfirst has helped them attain professional growth
82% feel learning new tools has added to their self-confidence
Chairs and Deans remain highly critical of CUNYfirst, whether or not system is deployed at their College (16% drop from 2008)
Overall 14% drop in satisfaction with training from 2008. However, users like on-the-job training (49%)
Users want to see more communication on the new system

## Slide 7: Go Live Decision Process
CUNYfirst Team
Data conversion Testing Training material and simulated environment Communication templates for student, faculty and staff User security Guidelines for infrastructure Risk review and mitigation
Campus Teams
Data validation and cleanup
Testing participation
Campus training using simulated environment
Student Orientation Finalize security based on users functional role Implement infrastructure guidelines Risk review and mitigation
Launch Decision Joint Meeting:
EVC Dobrin, College President & Key Advisors
Readiness Factors:
Data Conversion
Testing
Training
Data Security
Resource Availability
Campus Commitment to Launch
LAUNCH!

## Slide 8: Risk Assessment and Mitigation
Risks are identified by business process owners, CUNY campuses, and the CUNYfirst project team.
The impact of a risk and likelihood a risk will be realized is assessed and recorded in the risk assessment document.
Based on impact and likelihood of realization, a color is assigned for each risk by campus as follows:
Risk status and current disposition is reviewed and updated periodically by all involved stakeholders.
All risks must be formally accepted or mitigated prior to go-live.
High Risk
Low Risk
Mitigated Risk
Medium Risk

## Slide 9: Agenda
Welcome – Brian Cohen and Ron Spalter
Project Update – Suman Taneja
March Releases
July Release
Senior College Procurement – Satish Mishra
December Releases
Campus Solutions – Jim Anastasio
W3 Academic – W2 FA/WS – Graduate Admissions
Asset Management and Payroll – Satish Mishra
Best Practices & Lessons to share from the Colleges

## Slide 10: Campus Solutions Launch
Bio/Demo Duplicate Records Reconciliation
Importance of the bio/demo clean-up and duplicate records reconciliation.
Resources should either be dedicated to this effort or additional resources should be allocated for this task.
We have limited time and the SR campus SMEs already have a significant workload - due to DVs (2 week turn around for each review cycle) - data validation and clean-up, and UAT. All modules, including CS PRD schools and HCM, are adversely impacted by duplicate IDs in CF, as will W3 schools once in CF.
Pre-and Co-Requisite configuration
W3 colleges are encouraged to continue configuring their pre-and co-reqs in CF PRD
All the pre-and co-reqs need to be in place when W3 colleges begin creating Su/Fa 2013 Schedule of Classes in CF PRD.
Reminder
W3 Colleges should refrain from loading CAS/ASTA files into legacy systems for Summer or Fall 2013.

## Slide 11: Admissions Tracks
Limited Admissions
  Wave 3
  Wave 4
Graduate Full Admissions
  Lehman pilot
  Other graduate institutions
Undergraduate Full Admissions

## Slide 12: Limited Admissions
Wave 3 UAT underway
CAS/ASTA interfaces
  Already in PROD, testing configuration for Wave 3
GRAD leverage of ASTA interface
  HTR01 and BKL01 producing test files for UAT
Direct admits
  Already in PROD, testing configuration for Wave 3
Quick admits
  Already in PROD, testing configuration for Wave 3

## Slide 13: Graduate Full Admissions
Lehman pilot go-live for Spring 2014 semester
Four components working together
  Hobsons Connect for recruiting/prospecting
  CUNY On-Line Application (COLA)
    Configurable by:
      Institution
      Career
      Program
    Interface to Hobsons Connect for communications
    Ability to upload supporting materials

## Slide 14: Graduate Full Admissions
  Applicant gateway
    Replicates Student Self-Service for:
      Checklists
      Payments
      Accept/Decline admissions offer
  Delivered functionality
    Admissions processing through matriculation and term activation
    3C’s for management of checklists and communications

## Slide 15: Undergraduate Full Admissions
UAPC replacing ECM system and associated workflow including data input
OCS has added a resource
  Meeting with UPAC regarding decision engine have begun
Project plan calls for go-live in March 2014 for Spring 2015
  This may need to be reconsidered.

## Slide 16: C5 Requests
Campus Solutions C5 Requests | 
Add Math Regents and correct English Regents | Complete
Enable Archibus Data interface for all CS Pillars | Complete
Additional CS tables to I-805 and ADW | Complete
Outstanding CF Student Financials Balance report | Complete
Textbook Component Enhancement | Complete
Immunization Letters | Complete
CAS/ASTA suspense file handling | 85%
QBCC Placement Checkilst/Recipient | Ready for migration – under development by QBCC
Student Financials Aging Report | Request Update from Oracle
Hobsons Prospect/Recruitment interface | 95%-waiting for Hobsons feedback
Hobsons Enrollment Retain | TBD

## Slide 17: C5 Requests
Quick Admit Search Match force | Complete
Self Service Evaluate My Transfer Credit Evaluation | TBD
Self Service Transfer Credit Granted Display | TBD
Replicate holds across Business Units | TBD
Enrollment Verification and Graduation Status | CRM ticket to execute everyday submitted. 50%-Testing execution-requires Student advisment info
Pathways Workflow Approval | 95%
Pathways Extract to synchronize with legacy | 100%-pending migration to production
CUNY Law Aces-2 to CUNYfirst | TBD
Pathways major entry courses requirement | TBD
ASTA Immunization code and logic | 90%
Pathways Course Catalog display | 90%
Pathways schedule of classes display | 90%
CUNYfirst HCM/Student SUN1 LDAP synchronization | 90%
SR View Summary data with/wo SSN+DOB | Complete
FA View Only Data | 95%

## Slide 18: C5 Requests
EDS interface for application+commitment deposit | 80%
SAP Attempted Credits in lieu of Credits Earned | 100%-pending migration to prod
Undergraduate F Grade Forgiveness | Phase 1 analysis Underway
Aleph Patron Load | TBD
CAS/ASTA change to load SCD1 student group as potential SEEK/CD students | 90%
Brooklyn College daily DGW DAP22 extract | Further Discussion Required
Grad Data Update from CAS/ASTA | Phase 1 Complete/Phase 2 analysis required
Pathways TCE accommodation for requirement designations | 20%
Pathways Opt-IN Requirements - Notification | 20%
R2T4 Query and Update Disburse Aid Override | Submitted to Oracle for work/cost analysis
Third Party Customer Bills | TBD
Add subplans to ASTA | TBD
Faculty Center Grade Roster Date Closing | TBD

## Slide 19: Agenda
Welcome – Brian Cohen and Ron Spalter
Project Update – Suman Taneja
March Releases
July Release
Senior College Procurement – Satish Mishra
December Releases
Campus Solutions – Jim Anastasio
W3 Academic – W2 FA/WS – Graduate Admissions
Asset Management and Payroll – Satish Mishra
Best Practices & Lessons to share from the Colleges

## Slide 20: Procurement Update
Community Colleges
    In Production since June 2012
      Integrated with CUNYfirst GL for the CITY Procurement Transactions
      Student Refunds Checks being printed via Accounts Payables for QCC
    Resolution of items from the Business Managers meeting in Dec.2012
Senior Colleges
    All Senior Colleges to Go-Live in June 2013
    Functional Designs Done (SFS Interfaces, Customizations)
    System configurations already developed
    CEMLI Development is in progress
    Initial System Integration Testing has started
    UAT Plan and Test Scripts are being developed
    UAT to begin mid-March, 2013
    Training to start in May, 2013
Notes: 20

## Slide 21: Agenda
Welcome – Brian Cohen and Ron Spalter
Project Update – Suman Taneja
March Releases
July Release
Senior College Procurement – Satish Mishra
December Releases
Campus Solutions – Jim Anastasio
W3 Academic – W2 FA/WS – Graduate Admissions
Asset Management and Payroll – Satish Mishra
Best Practices & Lessons to share from the Colleges

## Slide 22: Asset Management
Legacy Insite System A stand alone system which tracks CUNY assets, artwork and sensitive equipment Stakeholders are Colleges, RF, CUNY Construction Fund, DASNY and Pitt Bonds Assets are loaded manually Access is limited to Property Managers for Inventory only Depreciation has to be calculated in an external system Yearly inventory is done to confirm assets viability and possession by the individual units Supports an asset tagging system with scanners to re-inventory the assets | CUNYfirst Asset Management module is integrated with CUNYfirst Procurement processes such as Purchasing, Accounts Payables and Receipts Same Stakeholders Tax-levy assets will be loaded automatically from AP/PO processes Access to assets view can be provided to various stakeholders Depreciation is calculated and tracked by the module Spreadsheet upload can be used to record assets that were not purchased through Procurement module such as NTL, DASNY and RF The system will be configured to support the yearly inventory and scanning of the asset tags Indirect cost recovery for Research

## Slide 23: Asset Management
Project Status
Current legacy functions have been identified for comparison with CUNYfirst Asset management module
Two CRP sessions have been conducted for various stakeholders with emphasis on integration with the Procurement module
Fit-Gap document FN.02 is being prepared by Oracle (Feb 1st week)
Projected Go-Live in 4th Quarter, 2013

## Slide 24: Payroll Update
Work Study Payroll
    In production since June 2012
      QCC Work Study Payroll Checks being generated since October, 2012
      Integrated with CUNYfirst General Ledger
    System Integration Testing in progress for Wave-2 colleges
    UAT scheduled for Wave-2 colleges in February, 2013
Tax-Levy Payroll
    Targeted for December 2013 with Brooklyn College as a pilot
    Multi Phase deployment approach for Risk Mitigation
    Inbound and Outbound Interfaces for the STATE Payroll only
    Integration with GL and Budget processes
Notes: 24

## Slide 25: Agenda
Welcome – Brian Cohen and Ron Spalter
Project Update – Suman Taneja
March Releases
July Release
Senior College Procurement – Satish Mishra
December Releases
Campus Solutions – Jim Anastasio
W3 Academic – W2 FA/WS – Graduate Admissions
Asset Management and Payroll – Satish Mishra
Best Practices & Lessons to share from the Colleges